## Beta Timesheet.txt
Master The Bass Timesheet
Week Commencing: | 2013-02-04
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Accelerometer changes | Inverted effect of accelerometer on LPF | N/A | 2 | N/A
| Sound generation | misc. work on sound generation | N/A | 3 | N/A
Stephen Rogers
Guy Howcroft
Ricky McGeehan | Accelerometer changes | Inverted effect of accelerometer on LPF | N/A | 2 | N/A
| Sound generation | misc. work on sound generation | N/A | 3 | N/A
Petro Tyurin |  |  |  |  | N/A
Jon Rankin | Sensor | Worked on tilt functionality | N/A | 10 | N/A
Week Commencing: | 2013-02-11
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Meeting | N/A | N/A | 1.5 | N/A
| Synth | Began work on synthesizer application | N/A | 2 | N/A
| Synth | Continued work on synthesizer prototype, investigated oscillators and LFOs | N/A | 3 | N/A
| Synth | Continued work on synthesizer prototype, sound working well and oscillator/LFO implementation in place. Low Pass Filter and Amplitude can now be modulated. Filter superclass has been changed (in prototype) to allow a filter to be applied with an attached oscillator. This implementation is to be defined per-filter. | N/A | 4 | N/A
| Synth | Continued work on synthesizer prototype. Code now mature and working well. No known bugs. Fixed bug in Low Pass Filter where amplitude was being reduced by a factor of ~5. | N/A | 4 | N/A
| Synth | Migrated code from synthesizer prototype to main trunk. Sound on trunk is intermittent when a filter is applied. Attempting to track down this bug. | N/A | 4 | N/A
| Synth | Implemented a mixing algorithm to play multiple sounds from different sources. This was added to Synth prototype. A bug has been identified where the audio being played is not consistent when being generated from a thread different to the main one. | N/A | 3 | N/A
Stephen Rogers
Guy Howcroft
Ricky McGeehan | UI | Design new UI with on-screen filter pads | N/A | 3 | N/A
| UI | Design bracket for speaker | N/A | 1 | N/A
| UI | New logo improvement | N/A | 1 | N/A
Petro Tyurin | New UI design | Initial design of the main screen | N/A | 12 | N/A
| Double Slider | Fixed Double Slider | N/A | 1 | N/A
| Filter toggle buttons | Adding filter buttons functionality | N/A | 3 | N/A
Jon Rankin | Sensor | Imroved tilt functionality | N/A | 20 | N/A
Week Commencing: | 2013-02-18
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Reasearch | Research into tone generation | N/A | 3 | N/A
| Audio Playback | Created prototype AudioTrackTest which plays consistent, good quality audio | N/A | 4 | N/A
| Synth | Modified Synth prototype to create consistent audio, ensured UI remains responsive | N/A | 4 | N/A
| Update Trunk | Migrated code to Trunk, added more waveforms, ensured all audio uses doubles and not floats | N/A | 6 | 8574485f5433ad65372273f6205315ca199091a9
Stephen Rogers | Calibration | Looked into using accelerometer calibration to give more useful values. | N/A | 7 | N/A
Guy Howcroft | Research display resizing | Research display resizing | N/A | 6 | N/A
| UI | Implement new UI | N/A | 6 | N/A
Ricky McGeehan | UI | Resize UI for use on tablets | N/A | 2 | N/A
| UI | Chopping up components of new UI into individual elements and saving them as PNGs. | N/A | 1 | N/A
Petro Tyurin | UI | Fixing UI layouts | N/A | 8 | N/A
| Touch functionality | Adding sound-on-touch functionality | N/A | 4 | N/A
Jon Rankin | Unknown | Unknown | Unknown | 10 | Unknown
Week Commencing: | 2013-02-25
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Meeting | N/A | N/A | 1 | N/A
| Recording functionality | Started work on recording functionality, put callbacks in place and modified FileManager class | N/A | 4 | c4c979d878fd188e4bcf7024ae2ac9897a47d122
| Recording functionality | Ffinished the majority of the recording code, popup menu now works, filename can be specified and the buffer wont overflow. | N/A | 8 | 629ff108678ee83013feb4b10d924fe8e0af98b8
| Meeting | N/A | N/A | 1 | N/A
| Synth | Integrated Low-Pass Filter with Synth prototype, tidied up filter code | N/A | 4 | N/A
Stephen Rogers
Guy Howcroft | Settings Menu | Added new pictures and resized for buttons | N/A | 3 | N/A
| Settings Menu | Added help manue and fix enable/disable filters | N/A | 4 | N/A
| Merged code | Merged code and changed record button | N/A | 6 | N/A
| Embedded font | Attempted adding embedded font | N/A | 4 | N/A
| Settings Menu | Added embedded font and changed Settings menu | N/A | 6 | N/A
Ricky McGeehan | UI | Resizing and changing the Settings Menu with new revised UI (+"chopping up"). | N/A | 2 | N/A
| UI | Extra changes to new Settings Menu. | N/A | 2 | N/A
| UI | Making app icon. | N/A | 2 | N/A
Petro Tyurin | Adjust touch functionality | Getting correct touch values | N/A | 4 | N/A
| Resizable UI | Making UI resizable | N/A | 15 | N/A
| Filter Buttons | Filter button fixes | N/A | 1 | N/A
Jon Rankin | Unknown | Unknown | Unknown | 12 | Unknown
Week Commencing: | 2013-03-04
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Filters | Added ocsillating filters | N/A | 3 | N/A
| Bug fixes | Bug fixes and general clean up of code | N/A | 5 | N/A
Stephen Rogers | New Sensor Code | Investigated and implemented new sensor code which can be implemented into the existing app. Include option that allows for calibration when the user holds the phone | N/A | 10 | N/A
Guy Howcroft | Settings Menu | Changed filter drop down boxes to match main screen | N/A | 3 | N/A
| Settings Menu | Improved the settings menu | N/A | 1 | N/A
| UI | Improved settings menu and main screen | N/A | 4 | N/A
Ricky McGeehan | UI | Makng icons for each waveform | N/A | 3 | N/A
Petro Tyurin | Settings Menu | Redesign Settings menu | N/A | 6 | N/A
| Improvements | Vibration functionality and slider improvements | N/A | 2 | N/A
| Code clean up | Removing unused code | N/A | 0.5 | N/A
| Increase efficiency | Change menu code to make loading Settings faster | N/A | 4 | N/A
Jon Rankin | Unknown | Unknown | Unknown | 10 | Unknown
Week Commencing: | 2013-03-11
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Sensor code integration | Worked with Steve (mainly) and Jon to get sound working with Tilt sensor. This will not integrate with the trunk currently. | N/A | 5 | N/A
| Intergration and clean up code | [1] Integrated audio code with main trunk. [2] Fixed bug in record where silence was buffered if the playback queue was full. [3] Removed warnings | N/A | 4 | [1] 5958d166b16a2b8a6abe690cf912351ca136a4b2 [2] 458e2098ada905f80ab4220ac9b2130be202631d [3] bcb11baf4187ec66e4561c381d91f424d2528d9c
Stephen Rogers | Sensor code integration | Worked with Luke (mainly) and Jon to get sound working with Tilt sensor. This will not integrate with the trunk currently. | N/A | 5 | N/A
Guy Howcroft | Improved UI | Added icons and waveforms and improved settings menu | N/A | 4 | N/A
Ricky McGeehan
Petro Tyurin | Text Changes | Various fixes of text display | N/A | 2 | N/A
| Settings menu changes | Improved Settings menu layout | N/A | 2 | N/A
| Help Menu | Added text to help menu | N/A | 1 | N/A
Jon Rankin | Unknown | Unknown | Unknown | 6 | Unknown
Week Commencing: | 2013-03-18
Name | Task Name | Description of work | Requirement number | Time Taken (hrs) | Git commit #
Luke Mitchell | Calibration | Integrated calibration for sensors into UI | N/A | 1 | 2d7ee2f38b3b794d3785bf684307f8a35f413903
Stephen Rogers | Filters | Investigated new filters to implement | N/A | 1 | N/A
| Calibration | Integrated calibration for sensors into UI | N/A | 1 | 2d7ee2f38b3b794d3785bf684307f8a35f413903
| Meeting | Total Meetings | N/A | 4 | N/A
| Time Sheet | Created Gamma Timesheet | N/A | 1.5 | N/A
Guy Howcroft | Meeting | Total Meetings | N/A | 10 | N/A
| Presentation | Made Presentation | N/A | 3.5 | N/A
Ricky McGeehan | Meeting | Total Meetings | N/A | 7 | N/A
| Presentation | Made Presentation | N/A | 3.5 | N/A
Petro Tyurin
Jon Rankin